## CYB 410 Project One Stepping
Green Thumb Risk Register
Positive Risk Response Options | Exploit | Share | Monitor | Accept | Probability/Impact | PI Score
Negative Risk Response Options | Avoid | Transfer | Mitigate | Accept | 1 | 1-3 | Low
Alternative Response Options | Contingency |  |  |  | 2 | 4-6 | Moderate
[5 empty] | 3 | 7-9 | High
Note: Colors in the heat map are conditionally formatted for your use in the template. Do not modify.
Risk | Something that has not happened but might
Issue | Something that has already happened
No longer active
Risk ID | Description | Risk Trigger | Risk Category | Probability (1-3) | Impact (1-3) | PI Score | Expected Result, No Action | Risk Response Type | Response Trigger | Response Description | Expected Impact of Response
| Description of the risk | How you know the risk is becoming an issue or has reached a point that requires action. | Group defines the types of risks (technological, financial, employee, etc.) | Group-sourced rough estimate of how likely this is to occur | Group-sourced rough estimate of how significant the impact of this risk will be if/when it becomes an issue | Probability multiplied by impact | What will happen if the risk becomes an issue and no action is taken | Decision made by group on how to respond to this risk (see above in blue) | How do you know it is time to put the response into play? | What is the response? | What do you expect will result from the response?
EXAMPLE | There is a chance that the project cost will exceed the amount that the company has budgeted for the work. | If the expected work remaining will cost more than $9,000 over budget, we will need to seek additional funding from management. | Financial | 2 | 3 | 6 | We will not be able to secure funding necessary to complete the project. Work may stop before MVP has been achieved. Product may never get to market and be deemed a total failure. | Mitigate | When estimated cost for MVP is within 5K of approved project total, we will begin seeking additional funding. | Meet with key stakeholders to review finished product, total spend to date, work remaining, and expected total spend. Ask for additional funding to complete work. | Given that our team has a mostly stable velocity and a proven ability to meet commitments and deliver value, we expect the answer to be yes provided the total amount of requests is less than $25K.
Ordering Supplies | There is a chance of not having access to the supplies necessary to support the nursery (including office supplies, fertilizer, additional inventory, and so on). | When supplies are low and online ordering is not possible due to internet issues or supplier stock problems. | Operational | 3 | 3 | 9 | The plants will suffer, leading to stunted growth and potential loss of inventory, negatively impacting sales and business operations | Mitigate | When supplies are down to one week's worth and online ordering is not possible. | Establish relationships with multiple suppliers and maintain a buffer stock of critical supplies to cover at least a week's worth of needs. | Reduction in the risk of supply shortages and continued business operations without significant interruptions.
Technology | There is a chance of not being able to access the the point-of-sale (POS) system or the licensing portal for regulated items (for example, pesticides and chemicals). | When the POS system or internet connectivity fails. | Technological | 2 | 3 | 6 | Customer transactions cannot be processed, leading to potential loss of sales and issues with inventory management. | Mitigate | When the POS system is down for more than 30 minutes or internet connectivity is lost. | Maintain a backup system and use manual transaction documentation to be entered later into the POS system. | Minimized disruption to sales and continued ability to process transactions and manage inventory.
Physical Security | There is a chance that if physical security is not in place, the opportunity for breaking and entering occurs. | When security cameras or alarm systems fail. | Security | 1 | 3 | 3 | Increased risk of theft or damage to the property and inventory. | Mitigate | When security equipment is malfunctioning or offline. | Regular maintenance of security equipment and use of backup power sources for security systems. | Increased security and reduced risk of theft or damage.
Asset Management | There is a chance of loss of quality control or loss of crop due to environmental factors or growing techniques. | When environmental controls fail or incorrect growing techniques are used. | Operational | 2 | 2 | 4 | Loss of crops and reduced inventory quality, impacting sales and profitability. | Monitor | When environmental controls or growing techniques are not performing as expected. | Regular audits and updates to growing techniques and environmental controls. | Maintained quality control and minimized crop loss.
Insurance | There is a chance of not having the proper insurance that would cover different situational issues related to business assets and employees. | When an incident occurs and insurance coverage is found to be inadequate. | Financial | 1 | 3 | 3 | Significant financial loss and inability to recover from incidents. | Transfer | When reviewing insurance policies and finding gaps in coverage. | Ensure comprehensive insurance coverage that addresses all potential risks. | Minimized financial loss and adequate coverage for all potential incidents.
Safety | There is a chance there could be an opportunity for mortal danger because of the nature of the business (for example, using ladders, forklifts, and pesticides). | When safety protocols are not followed or equipment malfunctions. | Operational | 2 | 3 | 6 | Increased risk of injury or fatal accidents among employees. | Mitigate | When safety violations are observed or reported. | Regular safety training and compliance checks to ensure all safety protocols are followed. | Reduced risk of accidents and improved safety for employees.